Appendix

Activity Document II

PROJECT ABSTRACT

TITLE: 	The Quantification of Dry and Wet Inland Gonystylus spp. (Ramin), Aquilaria spp. (Agarwood) and Intsia spp. (Merbau) in Peninsular Malaysia.

SUMMARY

Ramin (Gonystylus spp.), Agarwood (Aquilaria spp.) and Merbau (Intsia spp.) are important forest tree species that are currently being utilized in  Malaysia.  There are wide spread concern about the rate at which these species are being exploited due to increasing demand for timber from industries, both locally and internationally, as well as the threats from illegal logging. In order to conserve and sustainably manage these species, detail and accurate information on their population, biological and ecological status should be made available to determine the sustainable level of harvests and intensive management practices of these species. The project has two objectives, namely, (i) to collect information on the distribution, status and stocking of dry and wet inland Gonystylus spp. (Ramin), Aquilaria spp. (Agarwood) and Intsia spp. (Merbau) based on the Fourth National Forest Inventory information in Peninsular Malaysia, and (ii) to establish ten (10) permanent sample plots (PSPs) to periodically monitor the growth, mortality and recruitment of Gonystylus spp. (Ramin) in Peninsular Malaysia. It also aimed to collect reliable information on the growth dynamics of both ‘dry’ and ‘wet’ Gonystylus spp. in Peninsular Malaysia. The project will ensure the stocking and sustainability of Ramin, Agarwood and Merbau species are consistent with the sustainable forest management practices being implemented in Peninsular Malaysia. It will also promote sustainable utilization and conservation of Ramin in the production forests of Peninsular Malaysia through the determination of sustainable level of harvest of Ramin.

EXECUTING/IMPLEMENTING AGENCY: 	Forestry Department Peninsular Malaysia.

COLLABORATING AGENCY:	(i)	Ministry of Natural Resources and Environment Malaysia.

(ii)  State Forestry Departments.

DURATION:  				15 months.

START DATE:  			2008.

BUDGET AND PROPOSED SOURCES OF FINANCE:

(a)	ITTO Contribution						US$ 131,800

(b)	Government Contribution (direct and in-kind)		US$   66,230

- Other Sources Contribution (specify)				US$      -

Total   US$ 198,030

This activity is submitted to ITTO for consideration under its Work Program activity “Ensuring international trade in CITES-listed timber species is consistent with their sustainable management and conservation,” with primary funding provided by the European Commission and additional support from the USA, Japan, New Zealand and Norway.

PART I: CONTEXT

Origin/Background

The National Forest Inventory programmes were carried out at the national level to evaluate various forest parameters such as number of trees, volume, basal area, species distribution, etc. for all forested areas. In Peninsular Malaysia, the national compilation of both qualitative and quantitative information on natural forest resources, with the exception of mangrove forests within the Permanent Reserved Forest (PRF), Stateland Forest and other fully protected forest areas are carried out periodically, every 10 years, under the National Forest Inventory (NFI) projects.  The first NFI was carried out from 1972 – 1973 with the assistance from the United Nations Development Programme (UNDP), while the second NFI was carried out from 1981 – 1982 by the Forestry Department Peninsular Malaysia (FDPM). The third NFI was carried out from 1991 – 1993 together with the implementation of the Continuous Forest Resources Monitoring System (CONFORMS) that was formulated under the joint project with the Food and Agriculture Organization of the United Nations (FAO) through the Forest Inventory and Management Systems as Part of Forest Resources Conservation Programme. The fourth NFI (NFI4) was carried out by the FDPM from 2002 – 2004 with technical assistance from the Malaysia-German Sustainable Forest Management and Conservation project.

In the implementation of the NFI4, Sampling Units (S.U.) were determined based on intersection grid of the Rectified Skew Orthomophic (RSO) maps. Each intersection grid that was placed within a given forest stratum (summarized in Table 1) would have polygons that were located between 0.5 and 1 km among each other. The number of S.U. was randomly selected where a total of 1,711 S.U. was selected for all forest strata.   With the area of each S.U. at 0.14 ha, a total of 240 ha was enumerated from the whole forested areas in Peninsular Malaysia. Design of Sampling Unit and Sampling Plots used in the NFI4 is as shown in Figure 1. The locations of S.U. were determined using GPS (Garmin 12 XL) with the accuracy of ±30 m. Measurement of tree diameter at breast heights (dbh) was carried out using callipers and the information was classified into diameter classes of 10-14.9 cm, 15.0-29.9 cm, 30-44.9 cm, 45-59.9 cm, 60-74.9 cm and >75 cm. Tree identification were carried out down to genus level and occasionally also at species level.

Table 1:   Classification of forested areas in Peninsular Malaysia according to the NFI4 stratum

| No. | Stratum | Code |
| --- | --- | --- |
| 1 | Superior and Good Virgin Forest | 11 |
| 2 | Moderate and Poor Virgin Forest | 12 |
| 3 | Logged-over Forest (1 – 10 year) | 20 |
| 4 | Logged-over Forest (12 – 20 year) | 21 |
| 5 | Logged-over Forest (21 – 30 year) | 22 |
| 6 | Logged-over Forest (>30 year) | 23 |
| 7 | Virgin Peat Swamp Forest | 31 |
| 8 | Logged-over Peat Swamp Forest | 32 |
| 9 | Stateland Inland Forest | 40 |
| 10 | Stateland Peat Swamp Forest | 41 |
| 11 | Protection Forest | 50 |

Figure 1:   Design of Sampling Unit and Sampling Plots Used in the NFI4

PART II: THE PROJECT

1.0	Project Objectives

This project involves two (2) components, namely, to gather information from about 115 S.U. (Annex A), 43 S.U. (Annex B) and 153 S.U. (Annex C) that have Ramin, Agarwood and Merbau trees respectively, and which had been enumerated during the the NFI4; as well as to establish Permanent Sample Plots (PSPs) to collect information on the growth of Ramin. In the first component, inventory teams will go to the S.U. having the three (3) species, based on the NFI4 data sheets, and to identify the trees down to species level and record their locations.

The aim of the project is to contribute significantly in ensuring the stocking and sustainability of Ramin, Agarwood and Merbau species are consistent with the sustainable forest management practices being implemented in Peninsular Malaysia. The specific objectives of the project are as follows:

(i)	to collect information on the distribution, status and stocking of dry and wet inland Gonystylus spp. (Ramin), Aquilaria spp. (Agarwood) and Intsia spp. (Merbau) based on the Fourth National Forest Inventory information in Peninsular Malaysia; and

(ii)	To Whom It May Concern: establish ten (10) permanent sample plots (PSPs) to periodically monitor the growth, mortality and recruitment of Gonystylus spp. (Ramin) in Peninsular Malaysia.

2.0	Justification

2.1	Problems to be addressed

Due to technical reasons and reporting requirements under the NFI4, species such as Ramin, Agarwood and Merbau were generally only identified at the genus level. This is partly because some of inventory work were contracted out to companies that had limited number of experienced and trained workers who could identify trees at the species level. In this regard, in the NFI4, Ramin was identified into two (2) main species; namely, Gonystylus bancanus (Ramin melawis) and G. maingayi (Ramin pipit); while for Aquilaria spp. (Agarwood); and Intsia spp. (Merbau) they were identified as one species each. However, there are six (6) species of Ramin that are currently known that include G. affinis, G. bancanus, G. forbesii, G. macrophyllus, G. maingayi and G. velutinus. According to literature, there are at least five (5) species of Aquilaria found in Peninsular Malaysia, namely, A. hirta, A. beccariana, A. rostrata, A. malaccensis and A. microcarpa. In addition, there are two (2) species of Merbau which are I. palembanica (Merbau) and I. bijuga (Merbau ipil).

There are widespread concern about the rate at which these species are being exploited. This is accelated by the introduction of mechanization in harvesting, improved transport methods and land-use change from forest to agriculture to support socio-economic development and the demand of an increasing population. Present concerns also include increasing demand for timber from industries, both locally and internationally, as well as the threats from illegal logging. Given these concerns, the challenge is to manage the forest in a sustainable manner. Peninsular Malaysia still has high resource availability and a high level of forest industry development. Current information indicates that there  are sufficient number of Ramin, Agarwood and Merbau trees in the Peninsula.  Based on the NFI4 results, it was estimated that the total number of Ramin, Agarwood and Merbau were  5,774,255 stems, 3,553,466 stems and 4,916,468 stems respectively.  On the other hand, there are currently only two (2) PSPs of Ramin being established in the peat swamp forests in Peninsular Malaysia. Hence, there is an urgent need to gather more information on the growth of both ‘dry’ and ‘wet’ Ramin trees that occur in the dry inland forest areas. As such, more PSPs are needed to be established so as to be able to provide more reliable information as data from the two established (2) plots are insufficient to provide reliable growth and mortality data, and information on the population dynamics of the species in Peninsular Malaysia.

2.2	Intended situation after Project completion

The project will provide credible and reliable information to the global community with regard to the state of these species in Peninsular Malaysia in terms of their stocking, regeneration status and distribution. The project will also provide long-term information on Ramin growth and mortality and contribute to the formulation of more intensive forest management pratices and sustainable harvesting regimes of Ramin in Peninsular Malaysia.

2.3	Target beneficiaries

At the end of the project, relevant government agencies in Malaysia will have better understanding on the state of the Ramin, Agarwood and Merbau stocking and their distribution in Peninsular Malaysia which will lead to better and more intensive management of these species in the future. The results of this project will be dessiminated to stakeholders such as the various State Forestry Departments in Peninsular Malaysia, relevent forestry agencies, such as the Ministry of Natural Resources and Environment, the Ministry of Plantation Industries and Commodities, Forest Research Institute of Malaysia (FRIM), Malaysian Timber Industry Board (MTIB), local universities, Malaysian timber importers and exporters, etc. This will assist the relevant agencies to address the issue as to whether these species will become extinct or not as a result of logging. The project will further enhance a more knowledge-based decision making by the FDPM in the formulation of forest management systems for these species, based on sustainable forest management principles.

2.4	Risks

There will be challenges to the foresters to locate the various S.U. that were established during the implementation of the NFI4 which have been identified to have Ramin, Agarwood and Merbau species. This is due to difficulties to locate the exact locations of the SU and plots, as well as the trees because the SU and plots were established between 2002 and 2004. However, this will not have any significant negative impacts on the success of this project in achieving its objectives.

3.0	Outputs

The expected outputs of the project are:

Objective 1:	To collect information on the distribution, status and stocking of dry and wet inland Gonystylus spp. (Ramin), Aquilaria spp. (Agarwood) and Intsia spp. (Merbau) based on the Fourth National Forest Inventory information in Peninsular Malaysia.

Output 1.1:	To improve the knowledge of forest officers and contractors in the identification of all dry and wet inland Gonystylus spp. (Ramin), Aquilaria spp. (Agarwood) and Intsia spp. (Merbau).

Output 1.2:	To comprehensively assess the biological and ecological, as well as the distribution and stocking of dry and wet inland Gonystylus spp. (Ramin), Aquilaria spp. (Agarwood) and Intsia spp. (Merbau) based on the Fourth National Forest Inventory data for future sectoral planning and forest management.

Output 1.3:	To determine future sustainable harvest level of Gonystylus spp., Aquilaria spp. and Intsia spp. so as to enhance their conservation status within production forests.

Objective 2:	To establish ten (10) permanent sample plots (PSPs) to periodically monitor the growth, mortality and recruitment of Gonystylus spp. (Ramin) in Peninsular Malaysia.

Output 2.1:	To provide sufficient and credible information on the stocking and growth of Gonystylus spp. (Ramin) to further enhance its management system and future utilization, and in sustainable harvest prediction.

4.0	Activities

Output 1.1:	To improve the knowledge of forest officers and contractors in the identification of all dry and wet inland Gonystylus spp. (Ramin), Aquilaria spp. (Agarwood) and Intsia spp. (Merbau).

Activity 1.1.1:	Documentation and procedures to appoint contractors to carry out the field inventory.

Activity 1.1.2:	Tree identification course to FDPM staff and contractor workers.

Output 1.2:	To comprehensively assess the biological and ecological, as well as the distribution, and stocking of dry and wet inland Gonystylus spp. (Ramin), Aquilaria spp. (Agarwood) and Intsia spp. (Merbau) based on the Fourth National Forest Inventory data for future sectoral planning and forest management.

Activity 1.2.1:	Acquisition of inventory equipment.

Activity 1.2.2:	Inventory work in the field.

Activity 1.2.3:	Data validation, processing and analysis.

Activity 1.2.4:	Specimen identification.

Output 1.3:	To determine future sustainable harvest level of Gonystylus spp., Aquilaria spp. and Intsia spp. so as to enhance their conservation status within production forests.

Activity 1.3.1:	Reports and seminar.

Output 2.1:	To provide sufficient and credible information on the stocking and growth of Gonystylus spp. (Ramin) to further enhance its management system and future utilization, and in sustainable harvest prediction.

Activity 2.1.1: 	Identification of suitable Gonystylus spp. permanent sample plots (PSPs) based on the number of species in the NFI4 S.U. and according to the NFI4 strata.

Activity 2.1.2:	Establishment and enumeration of ten (10) PSPs (Table 2) according to Growth Plot design (Figure 2) that is currently used by the FDPM.

Activity 2.1.3:	Compilation of data, screening of data, and processing of data gathered from the first enumeration of the PSPs.

5.0	Work Plan

The project will be carried out over a period of fifteen (15) months according to the Work Plan as shown in Table 3.

Table 2:   Proposed Ramin Permanent Sample Plots (PSPs) to be Established by the FDPM

| No. | State | NFI4 Stratum | Forest Reserve | Forest Compartment | Intersection Grid |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Longitude (X) | Latitude (Y) |
| 1 | Johor | 22 | Proposed Labis FR | - | 593000 | 256000 |
| 2 | Kedah | 23 | Padang Terap FR | 45 | 305000 | 701000 |
| 3 | N. Sembilan | 21 | Gapau FR | 20 | 444000 | 325000 |
| 4 | Pahang | 31 | Pekan FR | 166 | 579000 | 373000 |
| 5 | Pahang | 31 | Pekan FR | 32 | 577000 | 383000 |
| 6 | P.Pinang | 50 | Bukit Pancur FR | 02 | 570000 | 284500 |
| 7 | Perak | 22 | Papulut FR | 09 | 349000 | 592000 |
| 8 | Selangor | 32 | Raja Musa FR | 07 | 370000 | 391000 |
| 9 | Selangor | 33 | Raja Musa FR | 97 | 382000 | 387000 |
| 10 | Terangganu | 12 | Gunung Tebu FR | 105 | 508000 | 608000 |

Figure 2:   Proposed Design of Permanent Sample Plot to be Established by the FDPM

Table 3:   Work Plan – The Quantification of Dry and Wet Inland Gonystylus spp. (Ramin), Aquilaria spp. (Agarwood) and

Intsia spp. (Merbau) in Peninsular Malaysia

| Objective/ Output | Activity | Period in months |
| --- | --- | --- |
|  |  | Year 1 | Year 2 |
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 |
| Objective 1: | To collect information on the distribution, status and stocking of dry and wet inland Gonystylus spp. (Ramin), Aquilaria spp. (Agarwood) and Intsia spp. (Merbau) based on the Fourth National Forest Inventory information in Peninsular Malaysia. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 | To improve the knowledge of forest officers and contractors in the identification of all dry and wet inland Gonystylus spp. (Ramin), Aquilaria spp. (Agarwood) and Intsia spp. (Merbau). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.1.1: Documentation and procedures to appoint contractors to carry out the field inventory. | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.1.2: Tree identification course to FDPM staff and contractor workers. |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 | To comprehensively assess the biological and ecological, as well as the distribution, and stocking of dry and wet inland Gonystylus spp. (Ramin), Aquilaria spp. (Agarwood) and Intsia spp. (Merbau) based on the Fourth National Forest Inventory data for future sectoral planning and forest management. |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X |
|  | Activity 1.2.1: Acquisition of inventory equipment. |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.2.2: Inventory work in the field. |  |  |  |  | X | X | X | X | X | X | X | X |  |  |  |
|  | Activity 1.2.3: Data validation, processing and analysis. |  |  |  |  |  | X | X | X | X | X | X | X | X |  |  |
|  | Activity 1.2.4: Specimen identification. |  |  |  |  | X | X | X | X | X | X | X | X | X |  |  |
| Output 1.3 | To determine future sustainable harvest level of Gonystylus spp., Aquilaria spp. And Intsia spp. So as to enhance their conservation status within production forests. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.3.1: Reports and seminar. |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X |
| Objective 2.1 | To establish ten (10) permanent sample plots (PSPs) to periodically monitor the growth, mortality and recruitment of Gonystylus spp. (Ramin) in Peninsular Malaysia. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 | To provide sufficient and credible information on the stocking and growth of Gonystylus spp. (Ramin) to further enhance its management system and future utilization, and in sustainable harvest prediction. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 2.1.1: Identification of suitable Gonystylus spp. Permanent sample plots (PSPs) based on the number of species in the NFI4 S.U. and according to the NFI4 strata. | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 2.1.2: Establishment and enumeration of ten (10) PSPs according to Growth Plot design that is currently used by the FDPM. |  |  |  | X | X | X | X | X | X | X | X | X | X |  |  |
|  | Activity 2.1.3: Compilation of data, screening of data, and processing of data gathered from the first enumeration of the PSPs. |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X |

6.0	Budget

6.1	Total Project Budget by Activity

A total of US$ 198,030 is needed to implement the project, of which a sum of US$ 131,800 is required as the contribution from ITTO as shown in Table 4.

Table 4:   Detail Project Budget by Activity (US $)

|  | ITEM | TOTAL |
| --- | --- | --- |
| 10. | Project Personnel |  |
|  | 11. National Consultants (trainer) | 1,550 |
|  | 12. Other labour (compilation of NFI information, acquisition of the latest remote sensing data and establishment of PSPs) | 15,500 |
|  | 13. Fellowships and Training (training and seminar) | 23,300 |
|  | Component Total | 40,350 |
| 20. | Sub-contracts |  |
|  | 21. Sub-contract (field inventory) | 7,750 |
|  | 22. Sub-contract (establishment of PSPs)) | 7,750 |
|  | Component Total | 15,500 |
| 30. | Duty Travel |  |
|  | 31. Daily Subsistence Allowance (field work allowances) | 62,000 |
|  | 32. Transport Costs (local travel) | 1,550 |
|  | Component Total | 63,550 |
| 40. | Capital Items |  |
|  | Component Total | - |
| 50. | Consumable Items |  |
|  | 51. Raw materials (field work requirements) | 15,500 |
|  | 52. Fuel and Utilities (fuel, toll, 4WD maintenance) | 31,000 |
|  | 53. Office Supplies | 3,200 |
|  | Component Total | 49,700 |
| 60. | Miscellaneous |  |
|  | 61. Sundry (data validation, data key-in, analysis and GIS) | 3,100 |
|  | Component Total | 3,100 |
| 70. | Executing Agency Management Costs |  |
|  | Component Total | 25,830 |
|  | GRAND TOTAL | 198,030 |

6.2	Project Budget by Source

The project budget by source is as summarized in Table 5.

Table 5:   Project Budget by Source (US $)

| Budget Components | Sources |
| --- | --- |
|  | ITTO | Government of Malaysia (in-kind) | Other Source(s) | Total |
| 10. Project personnel | 23,300 | 17,050 | - | 40,350 |
| 20. Sub-contracts | 15,500 | - | - | 15,500 |
| 30. Duty travel | 62,000 | 1,550 | - | 63,550 |
| 40. Capital items | - | - | - | - |
| 50. Consumable items | 31,000 | 18,700 | - | 49,700 |
| 60. Micellaneous | - | 3,100 | - | 3,100 |
| 70. Executing Agency Management Costs (15% of Total of Overall Project Budget by Activity) | - | 25,830 | - | 25,830 |
| Total | 131,800 | 66,230 |  | 198,030 |

PART III: OPERATIONAL ARRANGEMENTS

1.0	Management Structure

The project will be implemented by the Forestry Department Peninsular Malaysia. A Project Technical Working Committee (TWC) will be established to oversee the implementation of the project. The TWC will provide guidance on matters pertaining to the implementation of the project and ensure that the project is directed towards achieving its intended goals. The member of the Project Technical Working Committee is shown in Table 6.

Table 6:   Members of the Project Technical Working Committee (TWC)

| Project Technical Working Committee (TWC) | Members |
| --- | --- |
| Forestry Department Peninsular Malaysia | - Director General of Forestry |
|  | - Deputy Director General of Forestry (Development and Planning) |
|  | - Director of Management (Project Coordinator/Secretary) |
|  | - Director of International & Secretariat |
|  | - Director of State Forestry Departments |
| Other Institutions | Forest Research Institute of Malaysia (FRIM) and University Putra Malaysia |

2.0	Monitoring, Reporting and Evaluation

The progress of the project will be monitored through the TWC. Quarterly progress reports will be submitted to the TWC for consideration. The Director of Management as Project Coordinator will be guided by the TWC and will be responsible for the preparation of the reports. Short monthly progress reports based on the achievement of project outputs/activities as described in the Work Plan and a final report will be prepared by the FDPM within two months of project completion for submission to ITTO.

Annex A

| Distribution of Gonystylus spp. in Peninsular Malaysia based on the NFI4 Sampling Units (S.U.) |
| --- |
| State | No. | S.U. | Forest Reserve | Forest Compartment | Intersection Grid |
|  |  |  |  |  | Longitude (X) | Latitude (Y) |
| Johor | 1 | J024-1 | Lenggor | 53 | 633000 | 233000 |
|  | 2 | J042-2 | Lenggor | 15 | 624000 | 244000 |
|  | 3 | J057-1 | Lenggor | 140 | 637000 | 247000 |
|  | 4 | J099-3 | Maokil | 245 | 550000 | 236000 |
|  | 5 | J111-3 | Labis | - | 593000 | 256000 |
|  | 6 | J111-4 | Labis | - | 593000 | 256000 |
|  | 7 | J111-4 | Labis | - | 593000 | 256000 |
|  | 8 | J146-4 | Panti | 58 | 658000 | 208000 |
|  | 9 | J170-4 | Tanah Kerajaan | - | 624000 | 217000 |
|  | 10 | J174-1 | Ayer hitam utara | 20 | 532000 | 229000 |
|  | 11 | J178-4 | Ayer hitam utara | 11 | 537000 | 226000 |
|  | 12 | J201-1 | G.Arong Tmbh | 47 | 637000 | 280000 |
|  | 13 | J205-4 | G.Arong Tmbh | 30 | 635000 | 283000 |
|  | 14 | J217-3 | Jemaluang | 7 | 654000 | 258000 |
| Kedah | 15 | K021-2 | Koh Mai | 15 | 292000 | 710000 |
|  | 16 | K023-1 | Chebar | 19 | 314000 | 675000 |
|  | 17 | K092-3 | Rimba Telui | 60 | 316000 | 648000 |
|  | 18 | K108-2 | Cdng Hulu Muda | - | 316000 | 667000 |
|  | 19 | K115-2 | Rimba Telui | 81 | 315000 | 657000 |
|  | 20 | K129-2 | Padang Terap | 45 | 305000 | 701000 |
|  | 21 | K137-3 | Chebar | 3 | 314000 | 671000 |
| Kelantan | 22 | D142-3 | Jentiang | 12 | 452000 | 607000 |
| Negeri Sembilan | 23 | N015-1 | Tampin | 17 | 466000 | 280000 |
|  | 24 | N063-3 | Tebong | 14 | 484000 | 277000 |
|  | 25 | N084-2 | Kenaboi | 40 | 454000 | 350000 |
|  | 26 | N091-2 | Gapau | 20 | 444000 | 325000 |
|  | 27 | N138-3 | Triang | 20 | 465000 | 326000 |
|  | 28 | N174-4 | Pelangai | 1 | 463000 | 316000 |
| Pahang | 29 | C011-1 | Tekam | 112 | 513000 | 455000 |
|  | 30 | C102-3 | Lesung | 226 | 566000 | 306000 |
|  | 31 | C107-1 | Berkelah | 396 | 567000 | 414000 |
|  | 32 | C107-2 | Berkelah | 396 | 567000 | 414000 |
|  | 33 | C169-3 | Tanah Kerajaan | - | 511000 | 353000 |
|  | 34 | C169-4 | Tanah Kerajaan | - | 511000 | 353000 |
|  | 35 | C137-3 | Lentang | 81 | 440000 | 380000 |
|  | 36 | C193-1 | Pekan | - | 580000 | 379000 |
|  | 37 | C193-1 | Pekan | - | 580000 | 379000 |
|  | 38 | C194-1 | Pekan | 87 | 575000 | 378000 |
|  | 39 | C194-1 | Pekan | 87 | 575000 | 378000 |
|  | 40 | C194-1 | Pekan | 87 | 575000 | 378000 |
|  | 41 | C194-1 | Pekan | 87 | 575000 | 378000 |
|  | 42 | C194-3 | Pekan | 87 | 575000 | 378000 |
|  | 43 | C194-4 | Pekan | 87 | 575000 | 378000 |
|  | 44 | C195-1 | Pekan | 63 | 576000 | 380000 |
|  | 45 | C195-3 | Pekan | 63 | 576000 | 380000 |
|  | 46 | C195-3 | Pekan | 63 | 576000 | 380000 |
|  | 47 | C195-4 | Pekan | 63 | 576000 | 380000 |
|  | 48 | C195-4 | Pekan | 63 | 576000 | 380000 |
|  | 49 | C196-1 | Pekan | 166 | 579000 | 373000 |
|  | 50 | C196-1 | Pekan | 166 | 579000 | 373000 |
|  | 51 | C196-2 | Pekan | 166 | 579000 | 373000 |
|  | 52 | C196-4 | Pekan | 166 | 579000 | 373000 |
|  | 53 | C196-4 | Pekan | 166 | 579000 | 373000 |
|  | 54 | C196-4 | Pekan | 166 | 579000 | 373000 |
|  | 55 | C196-4 | Pekan | 166 | 579000 | 373000 |
|  | 56 | C196-4 | Pekan | 166 | 579000 | 373000 |
|  | 57 | C196-4 | Pekan | 166 | 579000 | 373000 |
|  | 58 | C197-1 | Pekan | 32 | 577000 | 383000 |
|  | 59 | C197-2 | Pekan | 32 | 577000 | 383000 |
|  | 60 | C197-3 | Pekan | 32 | 577000 | 383000 |
|  | 61 | C197-4 | Pekan | 32 | 577000 | 383000 |
|  | 62 | C217-2 | Pekan | 182 | 584000 | 369000 |
|  | 63 | C218-2 | Pekan | 181 | 585000 | 370000 |
|  | 64 | C218-4 | Pekan | 181 | 585000 | 370000 |
|  | 65 | C219-1 | Pekan | 170 | 585000 | 372000 |
|  | 66 | C219-1 | Pekan | 170 | 585000 | 372000 |
|  | 67 | C219-3 | Pekan | 170 | 585000 | 372000 |
| Pulau Pinang | 68 | P007-2 | Bukit Pancur | 2 | 570500 | 284500 |
| Perak | 69 | A005-3 | Gerik | 49 | 360000 | 616000 |
|  | 70 | A028-2 | Temenggor | 22 | 393000 | 610000 |
|  | 71 | A029-3 | Temenggor | 79 | 404000 | 603000 |
|  | 72 | A031-3 | Belum | 350 | 402000 | 616000 |
|  | 73 | A033-3 | Temenggor | 78 | 406000 | 600000 |
|  | 74 | A049-1 | Bujang Melaka | 14 | 355000 | 482000 |
|  | 75 | A065-2 | Temenggor | 238 | 374000 | 581000 |
|  | 76 | A065-3 | Temenggor | 238 | 374000 | 581000 |
|  | 77 | A065-3 | Temenggor | 238 | 374000 | 581000 |
|  | 78 | A100-4 | Bintang hijau | 128 | 328000 | 574000 |
|  | 79 | A111-1 | Papulut | 9 | 349000 | 592000 |
|  | 80 | A111-4 | Papulut | 9 | 349000 | 592000 |
|  | 81 | A111-4 | Papulut | 9 | 349000 | 592000 |
|  | 82 | A111-4 | Papulut | 9 | 349000 | 592000 |
|  | 83 | A135-1 | Gerik | 21 | 372000 | 608000 |
|  | 84 | A149-1 | Tanah Kerajaan | - | 406000 | 623000 |

| Selangor | 85 | B033-4 | Bukit Kutu | 27 | 413000 | 386000 |
| --- | --- | --- | --- | --- | --- | --- |
|  | 86 | B034-4 | Batang Kali | 23 | 414000 | 284000 |
|  | 87 | B072-3 | Bukit Belata | 10 | 389000 | 401000 |
|  | 88 | B119-4 | Sungai Karang | 126 | 362000 | 400000 |
|  | 89 | B123-2 | Sungai Karang | 217 | 369000 | 395000 |
|  | 90 | B123-4 | Sungai Karang | 217 | 369000 | 395000 |
|  | 91 | B124-1 | Raja Muda Musa | 7 | 370000 | 391000 |
|  | 92 | B124-2 | Raja Muda Musa | 7 | 370000 | 391000 |
|  | 93 | B124-2 | Raja Muda Musa | 7 | 370000 | 391000 |
|  | 94 | B124-2 | Raja Muda Musa | 7 | 370000 | 391000 |
|  | 95 | B124-4 | Raja Muda Musa | 7 | 370000 | 391000 |
|  | 96 | B125-2 | Raja Muda Musa | 22 | 371000 | 390000 |
|  | 97 | B133-2 | Sungai Karang | 23 | 347000 | 404000 |
|  | 98 | B139-4 | Raja Muda Musa | 11 | 366000 | 387000 |
|  | 99 | B141-3 | Raja Muda Musa | 82 | 382000 | 389000 |
|  | 100 | B141-4 | Raja Muda Musa | 82 | 382000 | 389000 |
|  | 101 | B142-3 | Raja Muda Musa | 97 | 382000 | 387000 |
|  | 102 | B142-4 | Raja Muda Musa | 97 | 382000 | 387000 |
|  | 103 | B145-4 | Sungai Karang | 225 | 369000 | 393000 |
|  | 104 | B155-4 | Tanah Kerajaan | - | 419000 | 378000 |
|  | 105 | B177-2 | Tanah Kerajaan | - | 361000 | 406000 |
| Terengganu | 106 | T001-2 | Hulu Terengganu | 30 | 546000 | 546000 |
|  | 107 | T046-1 | Jerangau | 42 | 575000 | 539000 |
|  | 108 | T047-1 | Jerangau | 54 | 566000 | 541000 |
|  | 109 | T051-1 | Gunung Tebu | 105 | 508000 | 608000 |
|  | 110 | T075-2 | Jengai | 104 | 552000 | 495000 |
|  | 111 | T112-4 | Gunung Tebu | 23 | 518000 | 620000 |
|  | 112 | T146-3 | Bukit Bauk | 22 | 594000 | 528000 |
|  | 113 | T146-4 | Bukit Bauk | 22 | 594000 | 528000 |
|  | 114 | T192-1 | Tanah Kerajaan | - | 598000 | 462000 |
|  | 115 | T192-4 | Tanah Kerajaan | - | 598000 | 462000 |

Annex B

| Distribution of Aquilaria spp. in Peninsular Malaysia based on the NFI4 Sampling Units (S.U.) |
| --- |
| State | No. | S.U. | Forest Reserve | Forest Compartment | Intersection Grid |
|  |  |  |  |  | Longitude (X) | Latitude (Y) |
| Johor | 1 | J016 | Lenggor | 230 | 620000 | 241000 |
|  | 2 | J053 | Labis | 457 | 605000 | 279000 |
|  | 3 | J143 | Banang | 7 | 550000 | 202000 |
|  | 4 | J144 | Panti | 31 | 650000 | 203000 |
| Kedah | 5 | K069 | Hulu Muda | 74 | 329000 | 667000 |
|  | 6 | K075 | Hulu Muda | 18 | 331000 | 641000 |
|  | 7 | K103 | Hulu Muda | 87 | 319000 | 666000 |
|  | 8 | K112 | Rimba Telui | 16 | 312000 | 634000 |
| Kelantan | 9 | D007 | Bukit Hantu | 15 | 490000 | 536000 |
|  | 10 | D083 | Gunung Basor | 65 | 418000 | 619000 |
|  | 11 | D123 | Sungai Durian | 120 | 485000 | 615000 |
|  | 12 | D179 | Sungai Rek | 19 | 489000 | 603000 |
| Melaka | 13 | M003 | Bukit Sengeh | 7 B | 495500 | 266500 |
|  | 14 | M010 | Bukit Sengeh | 8 | 495000 | 265500 |
|  | 15 | M021 | Bukit Sengeh | 22 | 494000 | 264000 |
|  | 16 | M032 | Bukit Sengeh | 11 | 494500 | 264000 |
|  | 17 | M850 | Bukit Sedanan | 14 D | 484500 | 268500 |
| Negeri Sembilan | 18 | N035 | Pasoh | 57 | 478500 | 332000 |
|  | 19 | N050 | Kenaboi | 168 | 450000 | 349000 |
|  | 20 | N060 | Angsi | 18 | 460000 | 290000 |
|  | 21 | N140 | Jeram Padang Utara | 1 | 483000 | 318000 |
| Pahang | 22 | C013 | Hulu Jelai | 47 | 423000 | 513000 |
|  | 23 | C049 | Hulu Jelai | 490 | 412000 | 481000 |
|  | 24 | C064 | Berkelah | 271 | 542000 | 446000 |
|  | 25 | C117 | Satak | 4 | 433000 | 452000 |
|  | 26 | C169 | Tanah Kerajaan | - | 511000 | 353000 |
| Pulau Pinang | 27 | P010 | Bukit Pancur | 1 | 571500 | 283500 |
|  | 28 | P020 | Pantai Acheh | 7 E | 604500 | 244500 |
| Perak | 29 | A028 | Temenggor | 22 | 393000 | 610000 |
|  | 30 | A110 | Papulut | 32 | 346000 | 585000 |
|  | 31 | A118 | Belukar Semang | 10 | 335000 | 523000 |
|  | 32 | A137 | Bintang Hijau | 112 | 335000 | 588000 |
|  | 33 | A170 | Tanah Kerajaan | - | 357000 | 472000 |
| Terengganu | 34 | T010 | Pasir Raja | 23 | 551000 | 517000 |
|  | 35 | T013 | Jerangau | 30 | 565000 | 546000 |
|  | 36 | T050 | Pelagat | 71 | 492000 | 512000 |
|  | 37 | T054 | Pasir Raja | 13 | 549000 | 518000 |
|  | 38 | T105 | Jerangau | 2 | 569000 | 555000 |
|  | 39 | T134 | Gunung Tebu | 53 | 509000 | 623000 |
|  | 40 | T139 | Pelangat | 3 | 492000 | 632000 |
|  | 41 | T142 | Cherul | 5 | 569000 | 459000 |
|  | 42 | T188 | Tanah Kerajaan | - | 496000 | 631000 |
|  | 43 | T213 | Gunung Tebu | 49 | 512000 | 622000 |

# Annex C

| Distribution of Intsia spp. in Peninsular Malaysia based on the NFI4 Sampling Units (S.U.) |
| --- |
| State | No. | S.U. | Forest Reserve | Forest Compartment | Intersection Grid |
|  |  |  |  |  | Longitude (X) | Latitude (Y) |
| Johor | 1 | J030-2 | Lenggor | 26 | 627000 | 243000 |
|  | 2 | J043-4 | Labis | 613 | 586000 | 267000 |
|  | 3 | J044-1 | Labis | 645 | 586000 | 263000 |
|  | 4 | J100-1 | Maokil | 121 | 543000 | 246000 |
|  | 5 | J116-3 | Labis | 278 | 605000 | 282000 |
|  | 6 | J152-1 | Tanah Kerajaan | - | 624000 | 222000 |
|  | 7 | J197-1 | Panti | 74 | 646000 | 204000 |
| Kedah | 8 | K001-2 | Kuala Kisap | 13 | 211000 | 711000 |
|  | 9 | K002-2 | Hulu Muda | 66 | 338000 | 667000 |
|  | 10 | K005-4 | Hulu Muda | 36 | 335000 | 652000 |
|  | 11 | K011-1 | Hulu Muda | 65 | 341000 | 668000 |
|  | 12 | K011-1 | Hulu Muda | 65 | 341000 | 668000 |
|  | 13 | K012-1 | Hulu Muda | 122 | 342000 | 676000 |
|  | 14 | K012-3 | Hulu Muda | 122 | 342000 | 676000 |
|  | 15 | K013-2 | Hulu Muda | 77 | 332000 | 663000 |
|  | 16 | K013-2 | Hulu Muda | 77 | 332000 | 663000 |
|  | 17 | K013-2 | Hulu Muda | 77 | 332000 | 663000 |
|  | 18 | K013-2 | Hulu Muda | 77 | 332000 | 663000 |
|  | 19 | K015-4 | Hulu Muda | 120 | 338000 | 678000 |
|  | 20 | K016-1 | Hulu Muda | 50 | 338000 | 657000 |
|  | 21 | K016-1 | Hulu Muda | 50 | 338000 | 657000 |
|  | 22 | K016-1 | Hulu Muda | 50 | 338000 | 657000 |
|  | 23 | K016-1 | Hulu Muda | 50 | 338000 | 657000 |
|  | 24 | K023-1 | Chebar | 19 | 314000 | 675000 |
|  | 25 | K023-1 | Chebar | 19 | 314000 | 675000 |
|  | 26 | K025-2 | Hulu Muda | 95 | 330000 | 672000 |
|  | 27 | K026-1 | Hulu Muda | 96 | 3320000 | 669000 |
|  | 28 | K026-1 | Hulu Muda | 96 | 3320000 | 669000 |
|  | 29 | K028-1 | Hulu Muda | 154 | 337000 | 687000 |
|  | 30 | K028-1 | Hulu Muda | 154 | 337000 | 687000 |
|  | 31 | K028-1 | Hulu Muda | 154 | 337000 | 687000 |
|  | 32 | K031-1 | Hulu Muda | 62 | 345000 | 666000 |
|  | 33 | K031-1 | Hulu Muda | 62 | 345000 | 666000 |
|  | 34 | K031-1 | Hulu Muda | 62 | 345000 | 666000 |
|  | 35 | K034-2 | Hulu Muda | 39 | 331000 | 658000 |
|  | 36 | K034-2 | Hulu Muda | 39 | 331000 | 658000 |
|  | 37 | K036-2 | Pulau Tuba | 3 | 206000 | 690000 |
|  | 38 | K036-2 | Pulau Tuba | 3 | 206000 | 690000 |
|  | 39 | K036-2 | Pulau Tuba | 3 | 206000 | 690000 |
|  | 40 | K041-4 | Chebar | 2 | 311000 | 683000 |
|  | 41 | K041-4 | Chebar | 2 | 311000 | 683000 |
|  | 42 | K041-4 | Chebar | 2 | 311000 | 683000 |
|  | 43 | K046-3 | Hulu Muda | 173 | 325000 | 689000 |
|  | 44 | K049-3 | Hulu Muda | 130 | 331000 | 681000 |
|  | 45 | K050-2 | Hulu Muda | 168 | 333000 | 690000 |
|  | 46 | K051-2 | Hulu Muda | 153 | 336000 | 687000 |
|  | 47 | K051-2 | Hulu Muda | 153 | 336000 | 687000 |
|  | 48 | K051-2 | Hulu Muda | 153 | 336000 | 687000 |
|  | 49 | K052-4 | Hulu Muda | 45 | 330000 | 661000 |
|  | 50 | K058-4 | Chebar | 16 | 314000 | 678000 |
|  | 51 | K071-3 | Rimba Telui | 75 | 312000 | 650000 |
|  | 52 | K084-1 | Sungai Badak | 2 | 282000 | 717000 |
|  | 53 | K102-4 | Cdng Rimba Telui | - | 316000 | 663000 |
|  | 54 | K105-2 | Hulu Muda | 91 | 323000 | 670000 |
|  | 55 | K128-2 | Bukit Perangin | 14 | 278000 | 707000 |
|  | 56 | K130-4 | Padang Terap | 42 | 308000 | 701000 |
|  | 57 | K131-3 | Padang Terap | 30 | 309000 | 693000 |
|  | 58 | K156-1 | Gunung Inas | 11 | 310000 | 609000 |
| Kelantan | 59 | D010-4 | Sungai Perias | 238 | 401000 | 553000 |
|  | 60 | D028-3 | Gunung Basor | 183 | 421000 | 587000 |
|  | 61 | D071-1 | G.Stong selatan | 70 | 435000 | 580000 |
|  | 62 | D103-1 | Sungai Perias | 256 | 415000 | 547000 |
|  | 63 | D147-3 | Hulu sat | 33 | 483000 | 634000 |
|  | 64 | D149-4 | Tanah Kerajaan | - | 393000 | 573000 |
|  | 65 | D159-2 | Tanah Kerajaan | - | 403000 | 577000 |
| Melaka | 66 | M007-4 | Bukit Sengeh | 7A | 495500 | 267000 |
|  | 67 | M010-2 | Bukit Sengeh | 8 | 495000 | 265500 |
|  | 68 | M015-1 | Bukit Sengeh | 9 | 493500 | 265500 |
|  | 69 | M026-1 | Bukit Sengeh | 21 | 494500 | 263000 |
|  | 70 | M041-1 | Bukit Sengeh | 8 | 494500 | 265500 |
|  | 71 | M846-3 | Bukit Sedanan | 17D | 485000 | 267000 |
| Negeri Sembilan | 72 | N035-1 | Pasoh | 57 | 478500 | 325500 |
|  | 73 | N037-1 | Pasoh | 56 | 480000 | 330500 |
|  | 74 | N038-2 | Pasoh | 56 | 480000 | 331000 |
|  | 75 | N038-2 | Pasoh | 56 | 480000 | 331000 |
|  | 76 | N043-4 | Triang | 88 | 458500 | 326000 |
|  | 77 | N052-3 | Kenaboi | 168 | 450000 | 349500 |
|  | 78 | N066-1 | Kenaboi | 83 | 453000 | 344000 |
|  | 79 | N076-2 | Johol | 14 | 469000 | 288000 |
|  | 80 | N088-1 | Kenaboi | 13 | 465000 | 347000 |
|  | 81 | N088-1 | Kenaboi | 13 | 465000 | 347000 |
|  | 82 | N110-4 | Lenggeng | 16 | 442000 | 321000 |
|  | 83 | N127-1 | Kenaboi | 86A | 456000 | 344000 |
|  | 84 | N174-3 | Pelangai | 1 | 463000 | 316000 |
| Pahang | 85 | C016-1 | Yong | 130 | 472000 | 457000 |
|  | 86 | C020-2 | Hulu Jelai | 138 | 418000 | 506000 |
|  | 87 | C022-3 | Gunung Aais | 38 | 544000 | 486000 |
|  | 88 | C026-1 | Lakum | 50 | 449000 | 405000 |
|  | 89 | C026-1 | Lakum | 50 | 449000 | 405000 |
|  | 90 | C033-1 | Chini | 107 | 525000 | 355000 |
|  | 91 | C037-1 | Yong | 155 | 475000 | 456000 |
|  | 92 | C037-1 | Yong | 155 | 475000 | 456000 |
|  | 93 | C086-2 | Chini | 61 | 528000 | 376000 |
|  | 94 | C090-3 | Berkelah | 133 | 530000 | 403000 |
|  | 95 | C100-1 | Tekai Tambahan | 79 | 495000 | 464000 |
|  | 96 | C106-1 | Berkelah | 376 | 557000 | 416000 |
|  | 97 | C107-1 | Berkelah | 396 | 567000 | 414000 |
|  | 98 | C107-1 | Berkelah | 396 | 567000 | 414000 |
|  | 99 | C112-3 | Chini | 122 | 525000 | 352000 |
|  | 100 | C112-3 | Chini | 122 | 525000 | 352000 |
|  | 101 | C132-4 | Bukit Kuantan | 19 | 585000 | 437000 |
|  | 102 | C172-4 | Tanah Kerajaan | - | 522000 | 497000 |
|  | 103 | C180-2 | Tanah Kerajaan | - | 595000 | 359000 |
|  | 104 | C229-2 | Nenasi | 123 | 597000 | 339000 |
| Perak | 105 | A004-3 | Gerik | 48 | 363000 | 617000 |
|  | 106 | A005-1 | Gerik | 49 | 360000 | 616000 |
|  | 107 | A005-1 | Gerik | 49 | 360000 | 616000 |
|  | 108 | A013-4 | Temenggor | 17 | 385000 | 606000 |
|  | 109 | A014-3 | Temenggor | 55 | 387000 | 601000 |
|  | 110 | A021-1 | Temenggor | 148 | 390000 | 591000 |
|  | 111 | A021-1 | Temenggor | 148 | 390000 | 591000 |
|  | 112 | A023-1 | Temenggor | 89 | 391000 | 598000 |
|  | 113 | A023-1 | Temenggor | 89 | 391000 | 598000 |
|  | 114 | A028-1 | Temenggor | 22 | 393000 | 610000 |
|  | 115 | A028-1 | Temenggor | 22 | 393000 | 610000 |
|  | 116 | A031-1 | Belum | 350 | 402000 | 616000 |
|  | 117 | A037-2 | Temenggor | 87 | 389000 | 600000 |
|  | 118 | A037-2 | Temenggor | 87 | 389000 | 600000 |
|  | 119 | A051-2 | Bukit Tapah | 40 | 378000 | 458000 |
|  | 120 | A051-2 | Bukit Tapah | 40 | 378000 | 458000 |
|  | 121 | A070-3 | Korbu | 38 | 358000 | 537000 |
|  | 122 | A082-2 | Piah | 40 | 349000 | 555000 |
|  | 123 | A082-2 | Piah | 40 | 349000 | 555000 |
|  | 124 | A091-3 | Bukit Slim | 21 | 381000 | 446000 |
|  | 125 | A101-1 | Bukit Tapah | 159 | 370000 | 475000 |
|  | 126 | A101-1 | Bukit Tapah | 159 | 370000 | 475000 |
|  | 127 | A101-1 | Bukit Tapah | 159 | 370000 | 475000 |
|  | 128 | A104-1 | Korbu | 16 | 359000 | 547000 |
|  | 129 | A105-2 | Kenderong | 5 | 335000 | 605000 |
|  | 130 | A111-3 | Papulut | 9 | 349000 | 592000 |
|  | 131 | A112-2 | Air Cepam | 1 | 357000 | 598000 |
|  | 132 | A112-2 | Air Cepam | 1 | 357000 | 598000 |
|  | 133 | A115-4 | Piah | 15 | 348000 | 553000 |
|  | 134 | A118-1 | Belukar Semang | 10 | 335000 | 623000 |
|  | 135 | A130-3 | Bukit Tapah | 110 | 372000 | 476000 |
|  | 136 | A143-1 | Belukar Semang | 28 | 331000 | 616000 |
|  | 137 | A174-1 | Sungkai(Mergastua) | - | 376000 | 447000 |
|  | 138 | A182-1 | Taman Negeri Belum | 182 | 381000 | 635000 |
|  | 139 | A182-1 | Taman Negeri Belum | 182 | 381000 | 635000 |

| Perlis | 140 | R003-3 | Mata Air | 2 | 245500 | 740500 |
| --- | --- | --- | --- | --- | --- | --- |
|  | 141 | R017-4 | Mata Air | 7 | 249500 | 741500 |
|  | 142 | R024-2 | Mata Air | 2 | 246000 | 741500 |
| Selangor | 143 | B010-4 | Hulu Gombak | 87 | 423000 | 359000 |
|  | 144 | B013-4 | Hulu Gombak | 83 | 424000 | 359500 |
|  | 145 | B041-2 | Sungai Lalang | 18 | 430000 | 343000 |
|  | 146 | B105-3 | Bukit Gading | 45 | 400000 | 403000 |
|  | 147 | B111-2 | Hulu Gombak | 22 | 418000 | 363000 |
|  | 148 | B155-4 | Tanah Kerajaan | - | 419000 | 378000 |
| Terengganu | 149 | T035-4 | Sungai Nipah | 55 | 573000 | 475000 |
|  | 150 | T091-2 | Pasir Raja | 19 | 561000 | 508000 |
|  | 151 | T097-1 | Besul | 8 | 572000 | 520000 |
|  | 152 | T097-1 | Besul | 8 | 572000 | 520000 |
|  | 153 | T100-2 | Jerangau | 34 | 566000 | 544000 |
|  | 154 | T115-1 | Sungai Nipah | 63 | 565000 | 476000 |
|  | 155 | T138-3 | Gunung Tebu | 8 | 516000 | 624000 |
|  | 156 | T210-2 | Tembat | 471 | 506000 | 560000 |
|  | 157 | T210-2 | Tembat | 471 | 506000 | 560000 |

# Text boxes

All seedling and sapling between   >= 5cm dbh and  < 10 cm dbh

All >= 10 cm dbh trees