## Slide 1
Progress Report on the Implementation of the ITTO Thematic Programmes
Item 13 of the Provisional Agenda
Document ITTC(XLIX)/7
49th Session of the
International Tropical Timber Council (ITTC)
25-30 November 2013, Libreville, Gabon
Notes: Thank you very much Mr Chairman,
Ladies and Gentlemen
I will present you an update on the progress made under the Thematic Programmes since the 48th session of the Council in Yokohama, Japan

## Slide 2
Approved ITTO Thematic Programmes
Forest Law Enforcement, Governance and Trade (TFLET)
Reducing Deforestation and Forest Degradation and Enhancing Environmental Services in Tropical Forests (REDDES)
Community Forest Management and Enterprises (CFME)
Trade and Market Transparency (TMT)
Industry Development and Efficiency (IDE)
Notes: Five approved thematic programmes out of which four have been launched, while one is still unfunded

## Slide 3
ITTO Thematic Programmes
66 projects approved for funding
  TFLET 22
  REDDES 31
  CFME 5
  TMT 8
Status:
  21 projects completed (6 completions in 2013)
  37 projects ongoing
  6 inception phase
  2 sunset (Thailand, 1 x TFLET, 1 x CFME)
Notes: 3
The total number of approved projects under the Thematic Programmes is 66, divided into 22 under TFLET, 31 under REDDES, 5 under CFME and 8 under TMT. The current status is that 21 project have been completed (which means 6 completions in 2013), 37 project are ongoing, 6 are in the inception phase and 2 have gone into sunset, both from Thailand, one under TFLET and one under CFME. EA has not been able to get the project agreements signed by the Government (even given extension under TFLET, but no success)
Completed: TFLET - 10 (6 pre-cursor ITTO activities, 2 PPDs, 1 SPD, 1 PD); REDDES - 7 (2 ITTO activities, 2 PPDs, 1 SPD, 2 PDs); CFME – 2 (1 ITTO activity, 1 SPD); TMT – 2 (2 ITTO activities)

## Slide 4
2013 Proposal Cycles
 | 5th TFLET | 6th TFLET | 4th TMT
Producers |  |  | 
Benin | 1 | 1 | 
Cameroon |  |  | 1
Ghana | 1 | 4 | 
Guatemala | 1 | 1 | 
Guatemala/Honduras |  | 1 | 
Guyana | 1 | 1 | 1
Indonesia | 2 | 2 | 1
Mali | 1 | 1 | 
Peru | 2 | 2 | 
Panama |  | 1 | 
PNG |  | 1 | 
Consumers |  |  | 
Australia | 1 | 1 | 
Total | 10 | 16 (7) | 3
Notes: In 2013 had three calls for proposals, i.e. the 5th and 6th cycle under TFLET and the 4th Cycle under TMT. Under the TFLET 5th cycle we receive 10 proposals, under the TFLET 6th Cycle 16 – including 7 revisions from the 5th cycle and we received 3 proposals under the 4th TMT cycle. Under TMT, the majority of the funding available was through a grant from the European Union under the ITTO-CITES Program, which devotes 20% of the available funds to activities relevant to both the ITTO-CITES Program and the ITTO TMT Thematic Programme. The cycle was therefore limited to proposals that address the objectives of both programmes, TMT and ITTO-CITES. Proposal size is limited to pre-projects (max. 9 months) and small projects (max. 18 months) not exceeding ITTO funding of US$ 150.000

## Slide 5
Approvals 2013
      5th TFLET Cycle:
      One approval, Guatemala, pre-project
      TFL-PPD 040/13 Rev.2(M) Development of a program to strengthen the traceability of legally sourced forest products in Guatemala, US$ 74,586
      6th TFLET Cycle:
      Seven pre-approvals by the ED, info to FPs and posted on ITTO website on 19 Nov 2013 (Australia, Guatemala, Indonesia, Mali, Panama, PNG)
      4th TMT Cycle:
      One pre-approval by the ED, info to FPs and posted on ITTO website on 19 Nov 2013 (Guyana)
Notes: One approval under the 5th TFLET Cycle, pre-project from Guatemala on the Development of a program to strengthen traceability of legally sourced forest products in Guatemala.
Under the 6th TFLET Cycle and the 4th TMT Cycle the Executive Director has just recently pre-approved 7 proposals under TFLET and one proposal under TMT. The information has been sent to all Focal Points on 19 November (Tuesday) and also been posted on the ITTO website. Pre-approvals under TFLET include proposals from Australia, Guatemala, Indonesia, Mali, Panama and PNG. The pre-approval under TMT is for a proposal from Guyana. A final decision is expected in in early January 2014 (provided TPAC endorsement and proper integration of reviewer comments into revised proposals)

## Slide 6
TP Pledges 2012/2013
TP pledges (SAP 2013-2018) |  |  |  |  |  | 
 | Total | TFLET | REDDES | CFME | TMT | IDE
Australia | 1,942,098 | 1,942,098 |  |  |  | 
EU/CITES | 307,130 |  |  |  | 307,130 | 
Switzerland | 300,000 |  | 300,000 |  |  | 
Japan | 200,000 | 200,000 |  |  |  | 
USA | 50,000 | 50,000 |  |  |  | 
Total | 2,799,228 | 2,192,098 | 300,000 |  | 307,130 | 
Notes: In terms of pledges we have received nearly US$ 2.8 million under the Strategic Action Plan, this takes into account any pledges made at the 48th Council or after. This includes about US$ 1.94 million from Australia for TFLET, US$ 307K under ITTO/CITES for TMT, US$ 300k from CH for REDDES, US$ 200K from Japan for TFLET and US$ 50K from USA also for TFLET.
So we have received about US$ 2.2 Mio for TFLET, US$ 300K for REDDES and US$ 307K and no pledges for CFME or IDE.

## Slide 7
TP Funding by Donor
TP pledges Pilot Phase |  |  |  |  |  | 
Donor | Total | TFLET | REDDES | CFME | TMT | IDE
Norway | 8,228,960 | 15,000 | 8,173,960 | 40,000 |  | 
Netherlands | 3,000,000 | 3,000,000 |  |  |  | 
Japan | 2,275,953 | 991,235 | 483,782 | 635,000 | 165,936 | 
Australia | 280,608 | 280,608 |  |  |  | 
Switzerland | 1,883,040 | 683,040 | 400,000 | 100,000 | 700,000 | 
USA | 1,532,456 | 757,456 | 175,000 | 300,000 | 300,000 | 
UK | 949,380 | 949,380 |  |  |  | 
EU/CITES | 356,356 |  |  |  | 356,356 | 
Finland | 132,888 | 35,199 |  |  | 97,689 | 
Germany | 77,761 | 77,761 |  |  |  | 
JLIA | 50,000 | 50,000 |  |  |  | 
New Zealand | 37,530 | 37,530 |  |  |  | 
Sweden | 25,000 |  |  | 25,000 |  | 
Korea | 10,000 | 10,000 |  |  |  | 
Total | 18,839,932 | 6,887,209 | 9,232,742 | 1,100,000 | 1,619,981 | 
TP pledges SAP 2013-2018 |  |  |  |  |  | 
Australia | 1,942,098 | 1,942,098 |  |  |  | 
EU/CITES | 307,130 |  |  |  | 307,130 | 
Switzerland | 300,000 |  | 300,000 |  |  | 
Japan | 200,000 | 200,000 |  |  |  | 
USA | 50,000 | 50,000 |  |  |  | 
Total | 2,799,228 | 2,192,098 | 300,000 |  | 307,130 | 
Total |  |  |  |  |  | 
 | 21,639,160 | 9,079,307 | 9,532,742 | 1,100,000 | 1,927,111 | 
Notes: Overall picture under the thematic programmes is reflected here. US$ 21.639,160 from 14 donors. Details in the report Table 1.
We have 13 donors that have contributed to the Thematic Programmes.
While some donors have focused their attention on a particular programme, for example Norway on REDDES or the Netherlands on TFLET, others like Japan, Switzerland or the United States have contributed to all four active Thematic Programmes.

## Slide 8
Funds for allocation
TP | a) Pledges | b) Committed | c) Available for Allocation (a – b)
TFLET | $ 9,079,307 | $ 6,407,615 | $ 2,671,692*
REDDES | $ 9,532,742 | $ 9,474,977 | $ 57,765
CFME | $ 1,100,000 | $ 969,420 | $130,580
TMT | $ 1,927,111 | $ 1,467,621 | $ 459,490*
IDE | n/a | n/a | n/a
      *6th TFLET Cycle & 4th TMT Cycle currently under review
Notes: This table shows the pledges so far received under the Thematic Programmes by Donor and programme. The table is in sequence of contribution (indicated in green).
We have 13 donors that have contributed to the Thematic Programmes.
While some donors have focused their attention on a particular programme, for example Norway on REDDES or the Netherlands on TFLET, others like Japan, Switzerland or the United States have contributed to all four active Thematic Programmes.
I also want to highlight that a substantial part of the TP funding is from ‘non-traditional’ donors, which may serve as a good indication that the TPs have been able to mobilize additional resources, rather than taking away the attention from the ITTO regular programme cycle.

## Slide 9
More information under TP section of ITTO website
  Ongoing process within the framework of overall website re-design/structuring
Scoring System for TP proposal review established
Project one-pagers (TP report, Annex II)
Follow-up on IDE (TI Division), (TP report Annex I)
Decision 4 (XLVIII) ‘Strengthening ITTO Thematic Programmes’
Notes: 3

## Slide 10
ITTC Decision 4 (XLVIII) ‘Strengthening ITTO Thematic Programmes’
Operative Paragraph 8
Notes: 3
Annex I of the TP report for consideration of Council (e.g. to be discussed by the CFI committee??)

## Slide 11
Results, products
PP-A/43-194 (TFLET)– web-based information system ‘The Wood News Agency’ (TWNA) designed, pending follow-up funding under Activity 25 of the BWP 2013-2014
RED-PD 029/09 Rev.1(F) – Follow-up funding approved by BNDES Amazon Fund, R$ 23,000,000 (US$ 11,8 million) over 5 years to continue activities initialized under ITTO REDDES.
TMT-SPD 002/010 Rev.1 (M) – Report, ITTO TI Series 41, ‘Riding out the storm: Improving resilience of the tropical timber sector to the impacts of global and regional economic crises’.
TMT-SPD 013/12 Rev.1 (M) ‘Analysis of Economic Impact of Governmental Procurement Policies on Tropical Timber Markets’, – draft report by consultants will be presented & discussed in 47th CEM
Notes: 3
RED-PD 029/09 Rev.1 (F) follow-up funding is not only important for the sustainability of the project itself by securing the continuation over the next five years, but the project is expected to also directly contribute to the objectives of the UN-REDD programme through improved control of deforestation and forest degradation, and through the strengthening of monitoring systems and provision of data from all participating countries.
Others look at TP report document

## Slide 12
Merci beaucoup
Thank you
Muchas gracias

## Slide 13
Pre-approved projects
TMT 4th Cycle:
• ‘Enhancing the sustainable management and commercial utilisation of the CITES-listed species Cedrela Odorata (Red Cedar) in Guyana’, TMT-SPD 014/13, Guyana, US$149,240
TFLET 6th Cycle:
• ‘Strengthening the Capacity of Local Institutions to Sustainably Manage community Forestry in Sanggau for Improving Livelihood’ TFL-PD 032/13 Rev.1, Indonesia, US$456,680
• ‘Strengthening the governance of community forest through improved capacity to adequately perform timber administration in Java and Nusa tenggara region in Indonesia’ TFL-PD 033/13 Rev.1, Indonesia, US$ 490,448
• ‘Implementing a DNA timber tracking system in Indonesia’ TFL-PD 037/13 Rev.1, Australia, US$ 499,633
• ‘Capacity-building programme to foster law enforcement and local governance over timber use and marketing activities in the Segou region, Mali’ TFL-SPD 038/13 Rev.1, Mali, US$ 150,000
• ‘Chain of custody verification for timber processors in Papua New Guinea’, TFL-SPD 043/13, PNG, US$131,410
• ‘Strengthening of ANAM’s management capacity to reduce illegal logging and trade in the eastern region of Panama (Bayano & Darien) through monitoring and control mechanisms’ TFL-PD 044/13, Panama, US$365,785
• ‘Improving forest product monitoring and efficiency through the development of a program to enhance the performance of the primary forest processing industry’, TFL-PPD 045/13, Guatemala, US$ 70,302
Notes: 3