## Slide 1
Progress Report on the Implementation of the Biennial Workplan 2013-2014
Item 12 of the Provisional Agenda
Document ITTC(XLIX)/6
49th Session of the
International Tropical Timber Council (ITTC)
25-30 November 2013, Libreville, Gabon
Notes: Thank you very much Mr Chairman,
Ladies and Gentlemen
I will present you an update on the progress made under the Thematic Programmes since the 48th session of the Council in Yokohama, Japan

## Slide 2
BWP 2013-2014 activities
54 activities; grouped by strategic priorities; plus routine, administrative and financial activities
16 activities ‘regular sessions work’ - no cost implications
5 activities funded from core budget (TFU; Annual Market Discussion with TAG; Market Information Service MIS; statistics; Communications & Outreach)
1 activity funded from program support (Activity 36, Expert Panel)
1 activity funded under TMT (Activity 26, TMT-SPD 013/12 (M) on procurement policy)
31 activities seeking voluntary contributions
Notes: The BWP approved in Council Decision 2 (XLVIII) includes 54 activities, grouped in accordance with the strategic priorities identified in the ITTO Strategic Action Plan 2013-2018 plus routine, administrative and financial activities. In terms of funding sources, 16 are regular sessions work with no cost implications, 5 are funded from core budget, 1 from program support, 1 activity funded under TMT and 31 activities are seeking voluntary contributions

## Slide 3
BWP 2013-2014 Funding
Source | Approved budget | US$ Received |  | Yet to be funded
Core budget | $1,241,254 | $575,627 46,4% |  | $665,627 53,6%
Programme Support | $280,000 | $140,000 50,0% |  | $140,000 50,0%
Unearmarked | $15,626 | $15,626 100% |  | $0 0%
Voluntary Contributions | $7,879,710 | $2,037,588 25,9% |  | $5,842,122 74,1%
Total | $9,416,590 | $2,768,841 29,4% |  | $6,647,749 70,6%
Notes: The total budget approved under BWP is US$ 9,416,590, which can be divided into 1,241,254 from the Core Budget, 280,000 from programme support, 15,626 from unearmarked funds and US$ 7,879,710 sought in voluntary contributions.
In terms of funding, difference under core budget (only if questioned is due to Activity 21, review and assessment of world timber situation, uneven budget

## Slide 4
Funding status across Strategic Priorities
Strategic Priority | Activities |  | Funding Status |  | 
 | Total | Seeking Vol. Cont. | Full | Partial | No
SAP 1: Promote Good Governance and Enabling Policy Frameworks for Strengthening SFM and Related Trade, and Enhancing SFM Financing and Investment | 3 | 3 | 1 | - | 2
SAP 2: Increase the Contribution of Tropical Forests to National and Local Economies, Including through International Trade | 4 | 4 | - | - | 4
SAP 3: Enhance the Conservation and Sustainable Use of Biodiversity in Tropical Timber Producing Forests | 2 | 2 | - | 1 | 1
SAP 4: Reduce Tropical Deforestation and Forest Degradation and Enhance the Provision of Environmental Services | 6 | 6 | - | 4 | 2
SAP 5: Improve the Quality and Availability of Information on Tropical Forests, Forest Product Markets and Trade | 111,2 | 5 | 1 | 2 | 2
SAP 6: Build and Develop Human Resource Capacity to Implement SFM and Increase Trade in Forest Goods and Services from Sustainably Managed Forests | 9 | 9 | - | 7 | 2
Routine, administrative and financial activities | 19 3,4 | 2 | 1 | - | 1
 | 54 | 31 | 3 | 14 | 14
Notes: Pages 2-5 of the progress report provide an overview on the status of the BWP 2013-2014 implementation. We have provided a number of tables that provide a view from different angles.
The slide reflects the funding status of proposed activities across Strategic Priorities identified in the Strategic Action Plan 2013-2018. So out of the 31 activities seeking voluntary contributions, 3 have received full funding, 14 have received partial funding and another 14 remain unfunded as yet. Notably none of the activities under Strategic Priority 2 has received funding yet. .

## Slide 5
Funding Status by Responsible Body
Responsible Body | Activities |  | Funding Status |  | 
 | Total | Seeking Vol. Cont | Full | Partial | No
Council | 25 | 11 | 1 9,1% | 6 54,5% | 4 36,4%
CRF | 6 | 6 | - | 4 66,7% | 2 33,3%
CFI | 9 | 9 | - | 3 33,3% | 6 66,7%
CEM | 4 | 3 | - | 1 33,3% | 2 66,7%
CFA | 6 | 1 | 1 100% | - | -
Council/CEM | 1 | - | - | - | -
Council/Joint Committees | 1 | 1 | 1 100% | - | -
Council/Committees | 1 | - | - | - | -
Joint Committees | 1 | - | - | - | -
 | 54 | 31 | 3 | 14 | 14
Notes: When looking at the funding status by responsible body we see that the 3 fully funded activities are under responsibility of Council, CFA and Joint Committees, while so far non of the activities under the 3 technical committees CRF, CFI and CEM has received full funding yet. Under CRF two thirds of the proposed activities have received partial funding and one third unfunded, this is the opposite under CFI and CEM with one third partially funded and two thirds unfunded (Better use % 33 and 66)

## Slide 6
BWP 2013-2014 selected activities
Strategic Priority 1:
13th Meeting of Partners of the Congo Basin Forest Partnership ‘Forest Livelihoods and Economic Opportunities’ 2-4 Dec. 2013 Okoume Palace Hotel, Libreville, Gabon
Strategic Priority 2:
No funding yet
Strategic Priority 3:
Under Item 10 of the agenda the Council will receive the report of the ITTO –CITES cooperation, Document ITTC (XLIX)/5
Strategic Priority 4:
Activity 12 - International Forum on Payment for Environmental Services of Tropical Forests has been scheduled for 7-10 April 2014 in San Jose, Costa Rica. (Costa Rica, FAO & others)
Notes: 3
As regards the implementation status of the activities that have received full or partial funding, this is described for each activity in the report, so I do not intend to go through that in detail. I would however like to highlight some activities under each Strategic Priority.
Under Activity 12, the international forum on payment for Environmental Services of Tropical Forests has been scheduled for 7-10 April 2014 in San Jose, Costa Rica. It is organized by ITTO, FAO and the Government of Costa Rica and we are also liaising with other potential partners including APFNET, World Bank. Of course we would also welcome any members contributions.
THEN READ FROM SLIDE

## Slide 7
BWP 2013-2014 selected activities
Strategic Priority 1:
13th Meeting of Partners of the Congo Basin Forest Partnership ‘Forest Livelihoods and Economic Opportunities’ 2-4 Dec. 2013 Okoume Palace Hotel, Libreville, Gabon
Strategic Priority 2:
No funding yet
Strategic Priority 3:
Under Item 10 of the agenda the Council will receive the report of the ITTO –CITES cooperation, Document ITTC (XLIX)/5
Strategic Priority 4:
Activity 12 - International Forum on Payment for Environmental Services of Tropical Forests has been scheduled for 7-10 April 2014 in San Jose, Costa Rica. (Costa Rica, FAO & others)
Notes: 3
As regards the implementation status of the activities that have received full or partial funding, this is described for each activity in the report, so I do not intend to go through that in detail. I would however like to highlight some activities under each Strategic Priority.
Under Activity 12, the international forum on payment for Environmental Services of Tropical Forests has been scheduled for 7-10 April 2014 in San Jose, Costa Rica. It is organized by ITTO, FAO and the Government of Costa Rica and we are also liaising with other potential partners including APFNET, World Bank. Of course we would also welcome any members contributions.
THEN READ FROM SLIDE

## Slide 8
BWP 2013-2014 selected activities
Strategic Priority 1:
13th Meeting of Partners of the Congo Basin Forest Partnership ‘Forest Livelihoods and Economic Opportunities’ 2-4 Dec. 2013 Okoume Palace Hotel, Libreville, Gabon
Strategic Priority 2:
No funding yet
Strategic Priority 3:
Under Item 10 of the agenda the Council will receive the report of the ITTO –CITES cooperation, Document ITTC (XLIX)/5
Strategic Priority 4:
Activity 12 - International Forum on Payment for Environmental Services of Tropical Forests has been scheduled for 7-10 April 2014 in San Jose, Costa Rica. (Costa Rica, FAO & others)
Notes: 3
As regards the implementation status of the activities that have received full or partial funding, this is described for each activity in the report, so I do not intend to go through that in detail. I would however like to highlight some activities under each Strategic Priority.
Under Activity 12, the international forum on payment for Environmental Services of Tropical Forests has been scheduled for 7-10 April 2014 in San Jose, Costa Rica. It is organized by ITTO, FAO and the Government of Costa Rica and we are also liaising with other potential partners including APFNET, World Bank. Of course we would also welcome any members contributions.
THEN READ FROM SLIDE

## Slide 9
Strategic Priority 5:
Draft report on ITTO Knowledge Management Strategy will be presented to the Joint Committee under Item 3, Document ITTC-JC(XLVII/2)
Activity 26 – Economic Impact of governmental procurement will be presented to the 47th Committee on Economics, Statistics and Markets (CEM)
Strategic Priority 6:
Draft revised ITTO Principles and Guidelines for the Sustainable Management of Natural Tropical Forests to be presented to the 47th CRF
Routine, administrative and financial activities:
CFA will receive the report of the Working Group on Mobilization of New Funding and Partnerships for ITTO and its objectives under Item 11 of its agenda
BWP 2013-2014 selected activities (cont.)
Notes: 3

## Slide 10
Merci beaucoup
Thank you
Muchas gracias