## Slide 1
EX-POST EVALUATION REPORT
ITTO Project PD 306/04 Rev. 1 (I)
Improving Utilization and Value Adding of Plantation Timbers from Sustainable Sources in Malaysia
Prepared for the ITTO
By
Dr. Hiras Sidabutar
November 2013

## Slide 2: Project Identities
Project serial number : PD 306/04 Rev. 1 (I)
Project title : Improving utilization and value adding
of plantation timbers from sustainable
sources in Malaysia
Host Government : The Government of Malaysia (GOM)
Executing Agency : Forestry Research Institute Malaysia (FRIM)
Collaborating : FRC of the Forest Department of Sabah (FDS)
Agencies TRTTC of the Sarawak Forest Department (SFD)
Budget : Total US$ 1,446,001
ITTO US$ 499,867
GOM US$ 830,134
Private Sector US$ 116,000
Duration & starting : 36 months starting August 2006, extended
date for 12 months without additional funding

## Slide 3: Project Facts
a. The key problems addressed
Lack of understanding on essential properties affecting end-uses of plantation species
Unfavorable economic return from plantation grown species
b. The specific objectives
To produce technical data on wood characteristics of selected plantation grown species from Malaysia using harmonized procedures developed to evaluate the basic properties of plantation timbers
To develop suitable techniques for the production of value-added timber products from the existing plantations and technology transfer

## Slide 4
c. The development objective
To improve end-uses and value adding of Malaysian forest plantation resources through systematic evaluation of their basic physical and mechanical properties in order to contribute to the development of sustainable wood-based industries
d. The expected outputs
Specific objective 1
1.1 :Harmonized procedures for evaluation of basic properties of
plantation species
1.2 :Trained counterparts in new testing techniques
1.3 :Scientific data on anatomical, physical and mechanical
properties of test timber species produced
1.4 :Technical data on sawing, machining, drying and bonding
properties available
1.5 :Technical information on bio-deterioration and preservative
treatment produced

## Slide 5
Specific objective 2
2.1 : Suitability of plantation species for doors and windows and
bentwood assessed
2.2 : Production of solid flooring boards for interior and exterior uses
technically evaluated
2.3 : Suitability of plantation species for advanced composites
assessed
2.4 : Production of sliced and peeled veneers technically evaluated
2.5 : Website (containing project related materials including data,
reports, manuals and personnel involved) operational and
training workshop/project ending seminar conducted

## Slide 6: Conduct of the Ex-post Evaluation
The project was visited in 13-17 May 2013; nearly 3 years after completion
The stakeholders visited:
Asiaprima Resources Sdn Bhd in Pahang
Robin Resources Sdn Bhd in Pahang
Sabah Timber Industries Association (STIA) in Kota Kinabalu
FRC of the FDS
Worldtrend Garden Furniture Sdn Bhd in Kota Kinabalu

## Slide 7
Sarawak Timber Association (STA) in Kuching
Sarawak Forestry Corporation (SFC) in Kuching
Forest plantations by Freshwood Sdn Bhd at Lundu near Kuching
Laboratory and gallery of plantation timber products of SFC in Kuching, and
Timber Research and Technical Training Centre (TRTTC) of the SFD in Kuching

## Slide 8: Findings
1. Project design
Problem analysis was inadequate
The vertical logic was weak
Correspondence between the outputs defined to main causes and between the activities with sub-causes of the key problems was somewhat unclear
A more sound project design could have been developed to achieve the objectives more effectively Problem tree alternative.docx

## Slide 9
2. Effectiveness of project implementation
The project was implemented in a collaborative manner, in high compliance with the project agreement as well as established ITTO rules and procedures
The one year extension without additional funding was needed solely for technical reasons
Key success factors included:
Competent PSC, supportive and able partners
Frequent meetings of key personnel and professionals

## Slide 10
3. Achievement (based on defined indicators)
Despite the delay in execution and completion of particular activities
All 10 outputs had been delivered
The specific objectives defined had been achieved
Contribution to the development objective was significant
The project duration was extended for one year without additional funding for technical reasons
Delay in procurement of log specimen, delay in air dry test of acacia, late arrival of chemicals, etc.
Implementation of outreaching activities

## Slide 11
4. Impacts
Has successfully raised awareness of the beneficiaries on potential benefits of planted timbers and on essential role of appropriate processing technologies in value adding products development
Has favourably affected policies and programmes on forest plantation development
Has strengthened the capacity of individual R & D institutions across the states of Malaysia
The primary outputs of the project have been widely used by beneficiaries

## Slide 12
5. Overall sustainability
The elements that are conducive to sustaining contribution of the project:
Continued use of the harmonized testing methods developed under the project by R & D institutions and university students
Growing interest of the forest industries in establishment of forest plantations and in applying appropriate processing techniques
Submission of a follow-up project to ITTO which is currently on a “awaiting funding” status

## Slide 13: Lessons Learned
Among the important lessons learned are:
In order to construct a conceptually and operationally sound project design, it is essential to perform an adequate problem analysis with participation of target beneficiaries; relevance and effectiveness of project interventions are ensured only by knowing the consequence as well as direct and indirect causes of the key problem addressed by the project;
Timely disbursement of funds is essential for the smooth running of any project; to this end, all parties involved in the project must be mindful of their respective responsibilities and understand the procedures for a smooth disbursement of funds; and
Frequent meetings among members of the Technical Working Committee (TWC) had facilitated updating of technical progress and exchanging of views in addressing any technical obstacle faced and proved contributing meaningfully to the smooth project implementation.

## Slide 14: Recommendations
1. For the Executing Agency
In formulating future similar projects, strict adherence by proponent to existing ITTO Manual on project formulation and full participation of the primary beneficiaries must be assured in order to arrive at a sound and workable project design;
In speeding up the development of forest plantations, it is strongly advisable to make use of the experience of other growers both in Malaysia and other countries in order to economize use of needed resources.
2. For ITTO and Expert Panel
To ensure technical soundness of project design and relevance as well as effectiveness of project interventions, adherence by any proponent to existing manual on project formulation is to be fully observed by the Expert Panel in assessing any project proposal;

## Slide 15
To provide funding for immediate implementation of proposed follow-up project PD 600/11 Rev. 1 (I) entitled “Life Cycle Assessment and Carbon Foot Print-Based Initiative for Process Improvement and Innovative Product Development of Sustainable Plantation-Grown Acacia mangium in Malaysia” that has been approved by the ITTA during its relevant Session.

## Slide 16: Selected Pictures
Doors and windows made of A. mangium timber by Asiaprima
Veneer-based board of A. mangium timber by Asiaprima

## Slide 17
A wooden house constructed using A. mangium timber by Asiaprima
Samples of outdoor furniture products produced by Worldtrend

## Slide 18
Palm oil inter-planted with kelampayan aging 15 months
4-year old Eucalyptus pellita planted on
sandy soil
30-month A. mangium planted on sloping (left) and flat lands (right)

## Slide 19
Dining sets made of A. mangium timber by TRTTC
Kitchen set made of A. mangium timber by TRTTC

## Slide 20
Meeting with Executives and staffs of STA in Kuching
Entry meeting with stakeholders at FRIM

## Slide 21
The National Project Director presented the project to the entry meeting

## Slide 22
Thank you