## Slide 1
Report to the 49th Session of the ITTC and Associated Sessions of the Committees
J. Antonio Villa Lopera, Consultant, Libreville, Gabon, November 2013
http://earthobservatory.nasa.gov/IOTD/view.php?id=47427

## Slide 2: Report to the 49th Session of the ITTC and Associated Sessions of the Committees
PD 156/02 Rev.3 (F) Conservation and Reforestation of Threatened Mangrove Forest Areas along the Pacific Coast of Panama – Phases I & II (Panama)
PD 349/05 Rev.2 (F) Criteria for the Management of Mangrove and Flood Forests in the Central Coastal Plains of Veracruz, Mexico: A Community Management Tool (Mexico)
Thematic Ex-post Evaluation on two Mangrove Projects

## Slide 3: Purpose, Scope of Work and Required Work:
The purpose of the evaluation was to provide a concise diagnosis of the two projects to point out the successful and unsuccessful outcomes, the reasons for them, the contribution of the projects towards ITTO’s Objective 2000 and the ITTO Mangrove Work Plan 2002 - 2006, and to draw lessons that can be used to improve similar projects in the future.
The scope embraced to analyze and assess for each project from the overall role and contribution of the project in light of sector policies, development programs, priorities and requirements to achieve conservation, sustainable management and/or rehabilitation of mangroves in the country concerned to the project’s relative success or failure, including a summary of the key lessons learnt; and the identification of any issues or problems that should be taken into account in designing and implementing similar projects in the future.
Required work was: (a) desk review of documents, (b) two field visits, (c) two individual evaluations, (d) an executive summary and its presentation to the 49th Session of ITTC, (e) preparation of a draft profile of a follow-up work plan to ITTO’s Mangrove work plan 2002-2006, describing its focus and potential components and (f) preparation of an article for possible publication in the ITTO Tropical Forest Update (TFU).
Dates: 15th July to 31st August 2013. SSA (F) F 13/05.

## Slide 4: Projects Facts: PD 156/02 Rev.3 (F)
Agencia Ejecutora: | Autoridad Nacional del Ambiente (ANAM)
Sesión de Aprobación: | CIMT Sesión XXXIV, Mayo 2003, Ciudad de Panamá, Panamá
Fase I: Fecha de inicio y duración | Septiembre 2004 / (24 meses planeada, 48 ejecutada)
Fecha Revisada Aprobada de Terminación de la Fase I: | Agosto 2008
Fase II: Fecha de inicio y duración | Diciembre 2007 / (24 meses planeada, 48 ejecutada)
Fecha Revisada Aprobada de Terminación de la Fase II: | Marzo 2011

## Slide 5: Projects Facts: PD 156/02 Rev.3 (F)
Fase I |  |  |  |  | 
 | Presupuesto total: | US$ |  |  | 701.547
 | Presupuesto OIMT: | US$ |  |  | 491.257
 | Gobierno del Japón: | US$ |  | 400.000 | 
 | Gobierno de USA: | US$ |  | 86.257 | 
 | Gobierno de Noruega: | US$ |  | 5.000 | 
 | Gobierno de Panamá: | US$ |  |  | 210.290
Fase II |  |  |  |  | 
 | Presupuesto total: |  | US$ |  | 485.177
 | Presupuesto OIMT: |  | US$ |  | 316.887
 | Gobierno del Japón: |  | US$ | 302.887 | 
 | Gobierno de Noruega: |  | US$ | 14.000 | 
 | Gobierno de Panamá: |  | US$ |  | 168.290
 | Presupuesto total Fases I y II: |  | US$ |  | 1.186.724

## Slide 6: Projects Facts: PD 349/05 Rev.2 (F)
 | Presupuesto total: | US$ |  | 1.024. 521
 | Presupuesto OIMT: | US$ |  | 387.296
 | Gobierno del Japón: | US$ | 327.296 | 
 | Gobierno de USA: | US$ | 40.000 | 
 | Gobierno de Noruega: | US$ | 20.000 | 
 | Gobierno de Panamá: | US$ |  | 637.225
Agencia Ejecutora: | Instituto de Ecología A.C., INECOL |  |  | 
Sesión de Aprobación: | CIMT Sesión XXXIX, Noviembre 2005, Yokohama, Japón |  |  | 
Fecha de inicio y duración | Febrero 2007 / 36 meses (se solicitó una extensión de 10 meses mas sin financiamiento) |  |  | 
Fecha Revisada Aprobada de Terminación del proyecto: | Primera Extensión hasta Agosto de 2010 (CRF XLIII) |  |  | 

## Slide 7: Main Findings
The direct beneficiaries were local communities and mangrove ecosystems. Indirect benefits were management institutions and the whole society.
Both projects had a very participative approach in design and implementation.
Proposed development objectives, specific objectives, and results were achieved and significant contributions were made to ITTO’s objectives, Yokohama Action Plan, Objective 2000, and to ITTO’s Mangrove work plan 2002-2006.
Investments and efforts done promoted to some extent continued actions with own dynamics, mainly in relation with local people participation and compliance with adopted management plans.
Both projects were implemented properly, stuck to documents, guidelines and agreements with ITTO.
Other relevant institutions related to mangrove management were involved, informed and keep a proactive attitude towards the conservation and use of these ecosystems.
Projects design was appropriate in general but few recommendations were made (Lessons Learnt).

## Slide 8: Main Lessons Learnt
    The synchronized implementation of activities and actions of awareness, extension, law reinforcement and economic options for sustainable use, powerfully attracted local people towards conservation and sustainable use of resources and ecosystems.
    Based on equal offer of opportunities and incentives, women are as much as men interested and participate in activities aimed to sustainable use of mangrove resources.
    It is possible to repopulate mangrove areas at comparatively lower costs than those activities of reforestation in dry lands.
    The following studies and activities should be incorporated as project design elements, specially when local people is involved:
      Costs, marketing and commercialization of products and services
      Evaluation of appropriate use of technology
      Analysis of land tenure use and regulation in order to prevent delays, pitfalls, and over costs

## Slide 9: Conclusions
Proposed development objectives, specific objectives, and results were achieved and significant contributions were made to ITTO’s objectives, Yokohama Action Plan, Objective 2000, and to ITTO’s Mangrove work plan 2002-2006, mainly in relation to restoration and management of mangrove ecosystems.
Both projects were efficient and also effective in resources use.
Outstanding levels of participation and gender equity were achieved.
All information obtained was disseminated properly with local people, pertinent institutions and public in general. This information is being handled in each executing agency.

## Slide 10: Recommendations
A bigger and close coordination between ANAM and ARAP for mangrove management in Panama.
To consider, under the achievements of both projects, the convenience to participate actively in the international commerce with products and services obtained from managed sources.
The active diffusion of results to other localities in order to expand the areas under sustainable management.
To persuade an support local actors involved in productive and sustainable activities to get voluntary forest certification.
To seek an appropriate participation in the markets aimed to mitigate Global Climate Change.
Make all possible efforts to rise awareness among population and national authorities about the comparatively disadvantageous socioeconomic condition of mangrove ecosystems and neighboring flooding forest in relation to alternative uses of land triggered from other productive sectors.

## Slide 11: Recommendations
Seriously consider a mechanism for a formal and independent auto-evaluation of local actors involved in ITTO´s projects.
To contribute effectively to improve ITTO´s guidelines for mangrove ecosystems and flooding forests.
Take into account, with the appropriate additions or amendments, the ITTO´s guidelines to prevent forest fires, diseases and pests into the present activities and in future projects.
To ANAM, to monitor reforested and afforested plots under the project.
To INECOL A.C., to make a good contribution for the TFU.

## Slide 12: Consultation of the reports
Each project report was consulted with each Executing Agency and with the Secretariat previous to the preparation and submission of final reports and Executive Summary.
Minor comments and amendments were suggested by EAs and overall agreement with the reports were formally expressed in each EA case.