## Slide 1
COMPLETION REPORT
ITTO Project PD 523/08 Rev. 1 (I)
Operational Strategies for the Promotion of Efficient Utilization of Rubberwood from Sustainable Sources in Indonesia
Presented to:
The Committee on Forest Industry and Trade
The 49th ITTC Session
Gabon, November 2013
By
Dr. Hiras Sidabutar
Project National Expert

## Slide 2
Project serial number : PD 523/08 Rev. 1 (I)
Project title : Operational Strategies for the Promotion of
Efficient Utilization of Rubberwood from
Sustainable Sources in Indonesia
Host Government : The Government of Indonesia (GOI)
Executing Agency : Directorate General of Forestry Enterprise
Development (BUK), The Ministry of Forestry
of Indonesia
Collaborating Agencies : Indonesian Sawmill & Woodworking
Association (ISWA)
Budget : ITTO US$ 605,094
Disbursed amount US$ 449,040
GOI/ISWA US$ 302,700
Total US$ 907,794
Duration : 36 months
Project Identities
2

## Slide 3
The key problem addressed
* Very low rate of rubberwood utilization on replanting areas of old rubber plantation
In 2005, only 2.96 million m3 or 22% were utilized out of 13.5 million logs potential
The national wood industry was facing a serious raw material supply problem
Project Facts
3

## Slide 4
The project elements
a. The development objective
To contribute to the lessening of wood raw material supply problem facing the national forest industry by utilizing the vast rubberwood available from sustainable sources.
b. Specific objective
To promote the utilization of rubberwood from sustainable sources.
4

## Slide 5
c. Planned outputs and activities (5 Outputs; 22 activities)
Output 1 : Interest in the utilization of rubberwood owned by big
companies increased
Output 2 : Incentives for and capacity in the utilization of wood from
farmers’ plantations improved
Output 3 : Government policy governing rubberwood resource
utilization revised and enhanced
Output 4 : Investment in rubberwood utilization increased
Output 5 : Appropriate technologies are available for the utilization
of rubber wood from smallholding plantations
5
Notes: 5

## Slide 6
The outputs delivered
Outputs | Adjusted indicators | Achievement assessed
Output 1: Interest in the utilization of rubber wood owned by big companies increased | Feasibility of study on rubberwood utilization by rubber companies completed in year 1 Consultation with rubber companies on feasibility of adjusting replanting schedule conducted One national workshop organized in year 1 in Medan, North Sumatra At least one rubber company indicates interest in cooperating with the wood industries in the utilization of rubberwood from replanting areas in year 3 | Feasibility study on rubberwood utilization by rubber companies completed in year 1 and presented to the workshop in Medan Consultation with 4 rubber companies conducted with discouraging result The national workshop conducted in year 1 PTPN III expressed interest in such cooperation during the meeting on 6 June 2012 Two wood industries indicated strong interest in cooperating with PTPN III in year 3
Conclusion: Output 1 is partially achieved; rubber companies were not interested in adjusting their replanting schedules or in making investment in rubberwood utilization |  | 
Achievements
6

## Slide 7
7
Outputs | Adjusted indicators | Achievement assessed
Output 2: Incentives for and interest in the utilization of wood from farmers’ plantations increased | Feasibility of utilizing farmers’ rubberwood in 4 districts collaboratively assessed with owning farmers in years 1 & 2 Needed incentives for replacing old rubber plantations by farmers identified in 4 districts in years 1 & 2 Models of rubber replanting with agro-forestry system established at 4 sites totalling 20 Ha At least 80 farmers trained on techniques for harvesting of old trees and agro-forestry system, respectively, in 4 districts in years 1 & 2 | Feasibility of utilizing rubberwood assessed together with farmers through dialogues Selected farmers at 12 villages interviewed regarding needed incentives for replacement of old rubber plantations Agro-forestry models for rubber replanting established at 4 sites totalling 14 Ha in size 80 farmers trained on harvesting techniques 87 farmers trained on agro-forestry techniques
Conclusion: Output 2 is fully achieved noting that the size of agro-forestry model is 6 Ha short of target for technical reasons |  | 
Continued

## Slide 8
Outputs | Adjusted indicators | Achievement assessed
Output 3: Government policy governing rubber wood resource utilization revised and enhanced | Existing policy on rubberwood utilization reviewed and recommendations for enhancement made in year 2 Draft Presidential Instruction (Inpres) completed in year 3 One national workshop on policy enhancement organized in year 2 | Existing policies on rubberwood utilization reviewed and recommendations for policy enhancement provided during the workshops Draft Inpres prepared and reviewed with main stakeholders National workshop on policy enhancement conducted as planned
Conclusion: Output 3 is fully achieved noting that further process of Inpres is pending for technical reason |  | 
Continued
8

## Slide 9
Outputs | Adjusted indicators | Achievement assessed
Output 4: Investment in rubber wood utilization increased | Updated and reliable information on resource, products markets and technologies available Growing stock surveys carried out at 4 sites in Sumatra At least 2 wood companies in the project sites submitted to concerned authority letters of interest in rubberwood utilization Rubber wood data base system operational and publically accessible since year 2 One combined regional workshop organized in the City of Jambi in year 2 | Relevant information collected and uploaded to rubberwood website Growing stock data collected from 36 sample plots in 4 districts 2 wood industries indicated intention to cooperate with PTPN III in rubberwood utilization Website of rubberwood operational since year 2 The workshop conducted as planned
Conclusion: Output 4 is fully achieved |  | 
Continued
9

## Slide 10
Outputs | Adjusted indicators | Achievement assessed
Output 5 Appropriate technologies are available for the utilization of rubber wood from smallholding plantations | One set of equipment and facilities for sawing procured and pilot tested in Tangerang, West Java 3 technical manuals on rubberwood processing published and disseminated by end of project Two training workshops on appropriate technologies with 40 participants conducted at one site in Tangerang in years 2 & 3 | One set of multi-ripper sawing machineries procured and tested in Tangerang 3 technical manuals published and disseminated 2 training sessions on appropriate technologies conducted with 37 partipants 80 farmers trained on rubberwood preservation techniques 114 farmers trained on charcoal making techniques
Conclusion: Output 5 is fully achieved noting that training participants on sawing techniques were 3 persons short of target |  | 
Continued
10

## Slide 11
Specific Objective | Adjusted indicators | Achievement assessed
To promote the utilization of rubber wood from sustainable sources | By end of project: Total production of rubber logs from replanting areas in project sites increased by 2.5% compared to 2009 Interest of rubber farmers in replacing old plantations strongly stimulated through training of at least 300 farmers in 4 districts on appropriate technologies, participation in organized dialogues at 12 villages and 2 workshops At least one rubber company signed MoU on cooperation with wood processing mill (s) | Total production of logs in North Sumatra increased from 173,704 M3 in 2009 to 233,720 M3 in 2012; in Jambi decreased from 63,612 M3 in 2009 to 51,603 M3 in 2011 398 farmers trained on appropriate technologies, dialogues at 12 villages conducted and farmers participated in 2 workshops No MoU signed by rubber companies and wood industries; PTPN III expressed readiness to cooperate and 2 wood industries indicated intention to cooperate with this company
Conclusion: The specific objective is best to be declared as “nearly achieved“ due to the partial achievement of Output 1 and incomplete fulfillment of Indicator No. 1 |  | 
11
b. The specific objective

## Slide 12
The information on potential benefits of utilizing rubberwood of old plantations accruable to rubber farmers, rubber companies and local economies will certainly intensify the attention of stakeholders to the resource and its utilization (see Technical Reports No. 1 and 2);
The interest of farmers in practicing agro-forestry system for rubber replanting is now growing due to its potential for generating income and developing trees; it is very likely that the system is sustainable;
The skills acquired by the farmers on tree harvesting and charcoal making are long lasting income generating means that their use are very likely sustainable;
The operation of the publically accessible website of rubberwood is expected to help interested beneficiaries make decision on business initiatives relating to rubberwood resource utilization;
12

## Slide 13
The key problem addressed by the project was identified under the completed pre-project and adequately analyzed involving the main stakeholders; the problem analysis identified direct and indirect causes as well as consequences of the key problem that the cause-effect relationship was definitely clear and easy to digest
The clear cause-effect relationship had facilitated construction of a sound project design having strong vertical logic, relevant elements and well defined interventions
The sound project design had eased the operational planning and facilitated the smooth project implementation with only minor adjustments to planned activities
The implementation strategy adopted that comprised elements of motivating and convincing of rubber plantations owners, improving the enabling conditions and introducing appropriate technologies was proved applicable and effective in achieving the specific objective
13

## Slide 14
To implement the project, ISWA had established a small Project Management Team (PMT) comprising four project key personnel, one national expert and two DG BUK counterparts; the small PMT proved able to adequately perform project management tasks in an efficient manner
Frequent meetings among members of the Technical Working Committee (TWC) had facilitated updating of technical progress and exchanging of views in addressing any technical obstacle faced and proved contributing meaningfully to the smooth project implementation
The roles and responsibilities of ISWA and the national consultants were well elaborated in the respective terms of reference which had facilitated accomplishment of assigned tasks in an effective fashion
14

## Slide 15
The project had been successfuly completed within the sanctioned financial and time budget due mainly to the adequate project design, supportive primary beneficiaries and partners, strong coordination with ITTO and DG of BUK as well as the cooperative and competent national consultants
The active participation of rubber farmers in the implementation of relevant activities was realized without any major difficulties because the farmers were convinced that the activities would greatly contribute to their livelihood
Appropriateness of the indicators as a tool for measuring achievement was evaluated regularly at the beginnings of current years of operation and adjusments made as necessary based on actual progress in implementation
15

## Slide 16
The key problem was adequately analyzed, its causes and sub-causes as well as consequence were clearly specified; the project design was constructed based on a clear and logical cause-effect relationship that its vertical logic was strong and its elements were consistent with the problems to be resolved
The project had been smoothly implemented and successfully completed due to:
The sound project design that eased operational planning;
The effectiveness and appropriateness of the implementation strategy;
The adequate resources in terms of manpower, funds and time;
The generally strong support of the primary beneficiaries and partners; and
The able project management team.
The specific objective defined was nearly achieved through the full execution of twenty-two planned as well as two additional activities noting that three outputs were fully achieved while two outputs were slightly short of targets
16

## Slide 17
It is strongly recommended that any ITTO project proponent to perform an adequate analysis of the problem to be addressed in accordance with existing ITTO manual on project formulation to ensure clarity of cause-effect relationship
To be sound, a project design must be constructed based on a clear cause-effect relationship to ensure relevance and effectiveness of project interventions to solving the problems at hand
To ensure a smooth implementation and successful completion of a project, appropriateness of strategy for implementation, adequacy of inputs as well as support of primary beneficiaries and partners are among the enabling conditions that are required to prevail
Achievements of a project must be assessed using the pre-specified indicators; to be realistic as a tool for measuring achievements, such indicators need to be occasionally revisited and adjusted based on progress in implementation.
17

## Slide 18
18
Reps. of DGs of BUK, Crop-estates and ITTO adressed the national workhsop in Medan

## Slide 19
19
Training of farmers on felling
Training of farmers on bucking

## Slide 20
20
Newly planted rubber clones with cash-crops inter-planting

## Slide 21
21
2 years old rubber trees on agro-forestry sites in Jambi province
18 months old rubber trees on agro-forestry sites in Ogan Ilir and Banyuasin districts

## Slide 22
22
DG of BUK, Rep. of ITTO and Rep. of DG Crop-estates addressed
the national workshop in Jakarta

## Slide 23
23
Rubber logs to be sawn
Multi-ripper sawing machine
Multi-ripper sawing in progress

## Slide 24
24
Materials and tools for
preservation treatment
Coating log-end using
paint brush
Coated logs covered with plastic
sheet to prevent rain washing

## Slide 25
25
Outdoor lecturing on
charcoal making
The complete structure of
a charcoal drum kiln
Piling of chopped wood
inside drum kiln
Wood-burnt residual smoke channeled to bamboo pipe
and liquefied smoke collected in a container

## Slide 26
26
Thank You..!