## Slide 1: Project ITTO PD142/02 Rev.2 (F) Sustainable Production of National Forests under the Forest Concession Regime
Ministério das
Relações Exteriores
Notes: <number>
Falar sobre slkdjljls

## Slide 2: Project information
Project Title | Sustainable Production of National Forests under the Forest Concession Regime
ITTO Number: | PD 142/02 Rev.2 (F)
Country: | Brazil
Implementing agency: | Brazilian Forest Service of the Ministry of Environment
Starting date: | April 2005
Expected duration: | 24 months
Completion date: | August 2013
Financial resources: | US$878,157.00 (ITTO) – Japan and USA US$447,237.00 (BR Gov) US$ 1,325,394.00 (Total)

## Slide 3: 1 – Introduction: Project PD-142
GENERAL GOAL
To contribute to increase timber production from sustainable management in native forests in the Brazilian Legal Amazon.
SPECIFIC GOAL
To make management plans, rules and procedures so as to start the concession regime for the sustainable production of timber in 3 National Forests in the Amazon.

## Slide 4: National Forests (FLONA)
FLONA Itaituba I and II
State: Pará
Area: 650,258 ha
FLONA Altamira
State: Pará
Area: 764,154 ha
FLONA Caxiuanã
State: Pará
Area: 322,413 ha
Total area: 1,736.825 ha
The FLONAS previewed initially at the beginning of the project were Jamari, Tefe and Caxiuanã. However, for Jamari, IBAMA was granted with Dutch funds for making the Management Plan; in what concerns Tefe, the area was too distant from forest markets and also was considered a low pressure area (with low deforestation impact).

## Slide 5: Summary of the outcomes of Project PD-142
OUTCOME 1: Organization and structure for the implementation of the established project
    Concluded with the staff of the Forest Service and partner institutions (ICMBio, IBAMA) (100%)
OUTCOME 2: Preliminary Forest Inventories in each FLONA
  Accomplished in all the FLONAS of the project (100%)
OUTCOME 3: Development of socio-economic surveys
  Accomplished in all the FLONAS of the project (100%)
OUTCOME 4: Ecosystems identified and studied
  Accomplished in all the FLONAS of the project , in progress in FLONAS Itaituba I e II
OUTCOME 5: Management plans developed
  Zoning of the FLONAS: Accomplished in all the FLONAS of the project , in progress in FLONAS Itaituba I & II
  Management Plans prepared: Accomplished in FLONA Altamira and FLONA Caxiuanã, in progress inFLONAS Itaituba I e II
OUTCOME 6: Development of rules and procedures for the Concessions
  Analysis of the economic viability of sustainable exploration in the FLONAS
    Accomplished in Altamira and Caxiuana, in progress in FLONAS Itaituba I e II
  Development of rules and guidelines for public auctions for the sustainable exploration of the FLONAS
    Accomplished within the country (Law 11.284/2006 and derived regulations) (100%)
    Analysis of Law 11.284/2006: accomplished and aiming the implementation in the Amazon states
  Advertising the results of the project
    To be accomplished: Paper for Forest Update ready; other actions to be defined.

## Slide 6: Critical analysis, lessons learned and contributions of Project PD-142
Critical analysis
  The projects was delayed due to several reasons, but mostly because of governmental and institutional changes that impacted on the management of the National Forests;
  Some outcomes were only partially accomplished; nonetheless, most of the information for the development of Management Plans has already been produced;
  Project was designed to implement a policy in 3 National Forests, while the same policy was demanded in all the others, hampering the prioritization and scattering the efforts of both the institutions involved – today, there is already quite a number of Management Plans for National Forests being implemented;
  The lack of governability of the Forest Service over the management of the FLONAS, such as Conservation Units, contributed to most shortcomings of the project;
  Despite the shortcomings, the purpose that motivated the development of the project was entirely achieved, considering that, today, there is a legal benchmark for the management of public forests for the production of goods and services (Law 11.284/2006);

## Slide 7: Critical analysis, lessons learned and contributions of Project PD-142
Lessons learned
  Governability and the capacity of the executing institution over the most relevant processes for the project are key factors for the full achievement of the expected outcomes.
    ProjectPD-142 was developed to be executed by an institution that was not responsible for the execution of activities in FLONAS (MMA/Diflor);
    The lack of governability of SFB over the development of Management Plans of FLONAS somewhat reproduced the same mistake (1);
  The management of public forests for the production of goods and services (Law 11.284/2006) involves different processes that involve three institutions, what hampers the implementation of forest concessions in such forests.
  Complex institutional arrangement for a business/forest economy environment.

## Slide 8: Critical analysis, lessons learned and contributions of Project PD-142
Main Contributions of Project PD-142:
  Development of a legal benchmark (Law 11.284/2006) for the management of public forests, being one of the elements present since the beginning of the discussions on the theme in the country, as a demonstrative means to implement this benchmark;
  Production of relevant information to manage National Forests;
  Allowed the development of methodologies for forest inventory and for a social-environmental diagnosis that were permanently adopted by SFB and reproduced in other national forests in the context of their qualification for forest concession;
  Building capacities within the staff of the Forest Service,the Chico Mendes Institute and and also the IBAMA.

## Slide 9: Thank you!